## Sheet1
NORTHPINE CITY IMPROVEMENT DISTRICT (NPC)
5 YEAR IMPLEMENTATION PLAN
1st July 2022 to 30th June 2027
PROGRAM 1 - NCID MANAGEMENT & OPERATIONS
NO. | ACTION STEPS | KEY PERFORMANCE INDICATOR | FREQUENCY per year | DURATION IN WEEKS, MONTHS OR YEARS |  |  |  |  | RESPONSIBLE | COMMENTS
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
1 | Appointment of relevant service providers | Appointment of appropriately qualified service providers. | 3 Years | 1 |  |  | 1 |  | NCID Board | Service providers to be reappointed or new providers to be appointed in last year of contract period by means of a competitive process. Well Documented.
2 | Board meetings | Quarterly Board meetings. | Quarterly | 4 | 4 | 4 | 4 | 4 | NCID Board | Quorum of directors present at every meeting. Feedback per portfolio. Keep minutes and file resolutions.
3 | Monthly Progressive Income and Expenditure Report to CCT | Submit reports to the CID Department timeously. | Monthly | 12 | 12 | 12 | 12 | 12 | NCID Manager | Refer to Finance Agreement. Submit reports to the CID Department by the 15th of the following month.
5 | Audited Annual Financial Statements | Audited Annual Financial Statements with an Unqualified audit finding. | Annually | 1 | 1 | 1 | 1 | 1 | NCID Manager | Submitted to the City by 31 August of each year.
6 | Communicate NCID arrears list | Board Members in arrears cannot participate in meetings. | Monthly | 12 | 12 | 12 | 12 | 12 | NCID Manager | Observe and report concern over outstanding amounts to Board and CID Department.
7 | Annual General Meeting | Annual feedback to members at AGM and complying with legal requirements | Annually | 1 | 1 | 1 | 1 | 1 | NCID Manager / NCID Board | Host successful AGM before 31 December.
8 | Submit Annual Report and Annual Audited Financial Statements to Sub-council(s) | Submit AFS and annual report to Subcouncil within 3 months of AGM. | Annually | 1 | 1 | 1 | 1 | 1 | NCID Manager / NCID Board | Submit proof of submission to CID Department.
9 | Successful day-to-day management and operations of the NCID | Monthly feedback to NCID Board. | Ongoing |  è |  è |  è |  è |  è | NCID Manager
10 | Maintain Website | Website with all the relevant documents as required by the By-Law and Policy | Ongoing |  è |  è |  è |  è |  è | NCID Board NCID Manager | Refer to Program 6-3.
11 | CIPC Compliance • Directors change • Annual Returns • Auditors change | CIPC Notifications of changes. | Annually | 1 | 1 | 1 | 1 | 1 | NCID Board | Changes in Directors & Auditors to be submitted to CIPC within 10 business days of change. Annual returns within 30 Business days after the anniversary date of the NPC registration.
12 | Monthly Reports to the Directors | Report back on all CID related business to be measured and signed off | Monthly | 12 | 12 | 12 | 12 | 12 | NCID Manager | Provide monthly reports to the Directors.
13 | Manage and monitor the C3 notification Process | Complete daily reports of C3 notifications and monitor outstanding issues | Monthly | 12 | 12 | 12 | 12 | 12 | NCID Manager | Follow up with sub-council in respect of outstanding C3 notifications
14 | Input to the Integrated Development Plan | Annual submissions to Subcouncil Manager | Annually | 1 | 1 | 1 | 1 | 1 | NCID Manager | October to February of every year.
15 | Input to the City Capital/Operating Budgets | Annual submissions to Subcouncil Manager. | Annually | 1 | 1 | 1 | 1 | 1 | NCID Manager | By September of each year.
16 | Communicate with property owners | Monthly newsletter | Monthly | 12 | 12 | 12 | 12 | 12 | NCID Manager | Keep property owners informed.
17 | Mediate issues with or between property owners | Provide an informed opinion on unresolved issues and assist where possible | Ongoing |  è |  è |  è |  è |  è | NCID Manager & City of Cape Town Departmental Managers and Law Enforcement
18 | Visit NCID members | Communicate and visit NCID members. | Bi-annually | 2 | 2 | 2 | 2 | 2 | NCID Manager | Refer also to Program 6-4
19 | Promote and develop NCID NPC membership | Have a NPC membership that represents the NCID community. Update NPC membership. Ensure that membership application requests are prominent on webpage | Ongoing |  è |  è |  è |  è |  è | NCID Manager / NCID Board
20 | Build working relationships with Subcouncil Management and relevant CCT officials and departments that deliver services in the Northpine area. | Successful and professional relationships with subcouncil management, Area Based Manager and City Departments resulting in enhanced communication, cooperation and service delivery | Ongoing |  è |  è |  è |  è |  è | NCID Manager
21 | CID renewal application and survey. | Submit a comprehensive renewal application for approval by the members and the City of Cape Town. | In year 5 |  |  |  |  | 1 | NCID Manager / NCID Board
22 | Annual Tax Compliance Status | Within one month after expiry date. | Annually | 1 | 1 | 1 | 1 | 1 | NCID Manager | Upload Tax Compliance Status via the eServices portal.
23 | Budget Review | Board approved budget review to the CCT by end of March. | Annually | 1 | 1 | 1 | 1 | 1 | NCID Manager | Submit Board minutes and approved adjustment budget to the CCT by end of March.
24 | All Directors to receive relevant CID Documents | At the 1st Board meeting after the AGM, supply all directors with all relevant CID documents | Annually | 1 | 1 | 1 | 1 | 1 | NCID Manager
25 | Allocation of portfolios | At the first Board meeting after the AGM, assign portfolios to Directors | Annually | 1 | 1 | 1 | 1 | 1 | NCID Manager / NCID Board
26 | Protection of Personal Information Act (POPIA) declaration | At the first Board meeting after the AGM, new Directors to sign the POPIA declaration | Annually | 1 | 1 | 1 | 1 | 1 | NCID Manager
27 | Declaration of interest | Ensure all Directors and Manager sign DOI at every Board Meeting | Bi-monthly | 6 | 6 | 6 | 6 | 6 | NCID Manager / NCID Board
28 | Vat reconciliation and tax returns | BI-monthly VAT returns and annual tax returns submitted to SARS on time | Bi-monthly | 6 | 6 | 6 | 6 | 6 | NCID Manager / NCID Board
29 | Annual approval of Implementation plan and Budgets | Obtain approval from members at AGM for Implementation Plan and Budget | Annually | 1 | 1 | 1 | 1 | 1 | NCID Manager / NCID Board
30 | Implement Business Plan | % of budget spent | Annually | 90% | 90% | 90% | 90% | 90% | NCID Manager / NCID Board | Ensure that the benchmark of 90% is attained.
PROGRAM 2 - NCID PUBLIC SAFETY / LAW ENFORCEMENT INITIATIVES
NO. | ACTION STEPS | KEY PERFORMANCE INDICATOR | FREQUENCY per year | DURATION IN WEEKS, MONTHS OR YEARS |  |  |  |  | RESPONSIBLE | COMMENTS
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
1 | Identify additional root causes of crime in conjunction with the SAPS, Local Authority and existing Public Safety service using their experience as well as available crime statistics | Update in Public Safety Management Strategy Plan | Ongoing |  è |  è |  è |  è |  è | NCID Manager/ Public Safety Service Provider | This is done comprehensively at the beginning of term and then modified continuously
2 | Review the Crime Threat Analysis of the CID area in conjunction with the SAPS | Update in Public Safety Management Strategy Plan | Ongoing |  è |  è |  è |  è |  è | NCID Manager/ Public Safety Service Provider
3 | Update strategies by means of an integrated approach to improve public safety | Update in Public Safety Management Strategy Plan | Ongoing |  è |  è |  è |  è |  è | NCID Manager/ Public Safety Service Provider
4 | In liaison with other Public Safety role players and the South African Police Service, identify any additional current Public Safety and policing shortcomings and update the public safety strategy and implement it effectively | Update in Public Safety Management Strategy Plan | Ongoing |  è |  è |  è |  è |  è | NCID Manager/ Public Safety Service Provider
5 | Approve the reviewed Public Safety Management Strategy with clear deliverables and defined performance indicators to guide safety services by the appointed service provider and evaluate levels of service provided. | Update the Public Safety Management Strategy with clear deliverables and defined performance indicators to guide public safety services by the appointed service provider and evaluate levels of service provided. | Revise as often as required but at least annually | 1 | 1 | 1 | 1 | 1 | NCID Manager/ Public Safety Service Provider and approved by the Board | This is done comprehensively at the implementation of the CID term and then modified continuously
6 | Maintain a manned centrally located office(s) open to the members and residents of the CID to request Public Safety assistance or report information | Appropriately manned and equipped office with skilled staff | Ongoing |  è |  è |  è |  è |  è | NCID Manager/ Public Safety Service Provider | As per Program 1-1
7 | Deploy Public Safety resources accordingly and effectively on visible patrols. Public Safety personnel and patrol vehicles to be easily identifiable | Effective safety and Public Safety patrols in the Northpine area. | Ongoing |  è |  è |  è |  è |  è | NCID Manager/ Public Safety Service Provider
8 | Utilise the "eyes and ears" of all Public Safety and gardening/street cleaning staff, as well as own staff, to identify any breaches | Incorporate feedback and information in Public Safety and safety initiatives of the NCID | Ongoing |  è |  è |  è |  è |  è | NCID Manager/ Public Safety Service Provider
9 | Assist the police through participation by NCID in the local Police sector crime forum | Incorporate feedback and information in Public Safety and safety initiatives of the NCID Report on any Public Safety information of the NCID to the CPF | Monthly | 12 | 12 | 12 | 12 | 12 | NCID Manager/ Public Safety Service Provider
10 | Monitor and evaluate the Public Safety strategy and performance of all service delivery on a quarterly basis | Report findings to the NCID Board with recommendations where applicable | Quarterly | 4 | 4 | 4 | 4 | 4 | NCIDManager/ Public Safety Service Provider/ SAPS Crime Intelligence Officer | Refer to Program 1-9
13 | On-site inspection of Public Safety Patrol officers | Report findings to the NCID Board with recommendations where applicable | Daily |  |  |  |  |  | NCID Manager/ Public Safety Service Provider
14 | Weekly Public Safety Reports from Contracted Public Safety Service Provider | Report findings to the NCID Board with recommendations where applicable Provide feedback to forum meeting | Weekly | 52 | 52 | 52 | 52 | 52 | Public Safety Service Provider | Incorporate into monthly management report to NCID Board
15 | Deploy CCTV cameras monitored by a CCTV Control Room | Effective use of CCTV cameras through monitoring | Ongoing |  è |  è |  è |  è |  è
16 | Appoint a CCTV Monitoring service provider | Appointment of appropriately qualified service providers. | 3 Years | 1 |  |  | 1 |  |  | Service providers to be reappointed or new providers to be appointed in last year of contract period by means of a competitive process. Well Documented. Refer to program 1-2.
17 | Register CCTV Cameras with the City of Cape Town | Cameras registered with the CCT | Ongoing |  è |  è |  è |  è |  è
|  |  |  |  |  |  |  | 
PROGRAM 3 - NCID CLEANSING & ENVIRONMENTAL INITIATIVES
NO. | ACTION STEPS | KEY PERFORMANCE INDICATOR | FREQUENCY per year | DURATION IN WEEKS, MONTHS OR YEARS |  |  |  |  | RESPONSIBLE | COMMENTS
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
1 | Review a cleansing strategy document | Update the Cleansing strategy document with clear deliverables and defined performance indicators to guide the cleansing and delivery. | Annually | 1 | 1 | 1 | 1 | 1 | NCID Manager/ Cleansing Service Provider | Revise as often as required but at least annually.
2 | Review the Cleansing Strategy to guide cleansing and delivery | Monitor and evaluate the cleansing strategy and performance of all service delivery on a quarterly basis | Quarterly | 4 | 4 | 4 | 4 | 4 | NCID Manager/ Cleansing Service Provider
3 | Appoint Cleaning service provider | Appointment of appropriately qualified service provider. | 3 Years | 1 |  |  | 1 |  | NCID Manager / NCID Board | Service providers to be reappointed or new providers to be appointed in last year of contract period by means of a competitive process. Well Documented. Refer to program 1-2.
4 | Additional litter bins and emptying of litter bins. | Quarterly status reports to CCT regarding progress of identified shortcomings | Quarterly | 4 | 4 | 4 | 4 | 4 | NCID Manager/ Solid Waste Department
5 | Cleaning of streets and sidewalks in the Northpine area | Cleaning each of the streets within the CID boundary at least once within every two month period | Bi-monthly | 6 | 6 | 6 | 6 | 6 | NCID Manager/ Cleansing Service Provider
6 | Health and safety issues reported to CCT with C3 notifications | Monthly evaluations and inspections of reported C3. Report to the Board. Provide an improved healthy urban environment in the ______ | Ongoing |  è |  è |  è |  è |  è | NCID Manager/NCID Board | Follow up with sub-council in respect of outstanding C3 notifications
7 | Monitor and combat Illegal dumping | Removal of illegal dumping when required and applying applicable penalties through law enforcement against transgressors. Report to the Board. | Ongoing |  è |  è |  è |  è |  è | NCID Manager/ Cleansing Service Provider/ Law Enforcement Officers/NCID Board
8 | Identify environmental design contributing to grime such as wind tunnels | Quarterly evaluate the causes of waste, measures implemented and identification of remedial actions. Report to the Board. | Quarterly | 4 | 4 | 4 | 4 | 4 | NCID Manager/ Cleansing Service Provider/NCID Board
9 | Promoting waste minimization through education and awareness on waste and water pollution | Monthly evaluations and inspections. Report findings to Board. | Ongoing |  è |  è |  è |  è |  è | NCID Manager/ Cleansing Service Provider, Solid waste Department
10 | Encourage property owners to act responsibly in terms of waste management and encourage recycling initiatives | Monthly evaluations and inspections. Report findings to the Board. | Ongoing |  è |  è |  è |  è |  è | CID Manager / Solid Waste Department
11 | Local NGO to assist in cleaning programs where applicable | As required coordinate cleaning programs and report to the Board | Ongoing |  è |  è |  è |  è |  è | CID Manager | Refer to program 4-4 and 5-2
12 | Recycle waste | Recycle waste collected by cleaning staff where possible and report progress to the Board. | Ongoing |  è |  è |  è |  è |  è | NCID Manager/ Cleansing Service Provider
13 | Greening campaigns - Arbor Day | Advise the NCID Board and provide recommendations where applicable | Annually | 1 | 1 | 1 | 1 | 1 | NCID Manager
PROGRAM 4 - NCID URBAN MANAGEMENT INITIATIVES
NO. | ACTION STEPS | KEY PERFORMANCE INDICATOR | FREQUENCY per year | DURATION IN WEEKS, MONTHS OR YEARS |  |  |  |  | RESPONSIBLE | COMMENTS
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
1 | Identify problem areas with respect to: a. street lighting; b. missing drain covers / cleaning of drains c. maintenance of road surfaces; sidewalks d. cutting of grass / removal of weeds e. road markings / traffic signs | Update Urban management plan with clear deliverables and defined performance indicators to guide delivery – Report monthly to the Board | Ongoing Monthly reporting to the Board. |  è |  è |  è |  è |  è | NCID Manager | Use the established service levels to design the provision of supplementary services without duplication of effort.
2 | Identify and report damage to City of Cape Town infrastructure in the following services: a. Street lighting b. Dumping c. Refuse Removal d. Waterworks e. Sewerage f. Roads and Storm water g. Traffic signals and line painting h. Pedestrian safety i. Road repairs | Monitor and evaluate. Report findings to the NCID Board with recommendations where applicable | Daily / weekly and monthly reports to the C3 notification process and daily recording of references in the register |  è |  è |  è |  è |  è | NCID Manager
3 | Compile a list of prioritized needs to enhance the objectives of the CID and liaise with the relevant departments to correct | Monitor and evaluate the plan and performance of all service delivery on a quarterly basis. Report findings to the NCID Board with recommendations where applicable | Monthly | 4 | 4 | 4 | 4 | 4 | NCID Manager
4 | Work in conjunction with local social welfare and job creation organization and develop the delivery of the supplementary services to improve the urban environment | Review and development of a long-term sustainable work program | Ongoing |  è |  è |  è |  è |  è | NCID Manager | This is done comprehensively at the term renewal and then modified and managed continuously Also refer to Program 5-2 and 3-11
5 | Illegal Poster Removal Notify and monitor the removal of illegal posters by the City of Cape Town | City of Cape Town infrastructure free from illegal posters | Ongoing |  è |  è |  è |  è |  è | NCID Manager
PROGRAM 5 - NCID SOCIAL INTERVENTION INITIATIVES
NO. | ACTION STEPS | KEY PERFORMANCE INDICATOR | FREQUENCY per year | DURATION IN WEEKS, MONTHS OR YEARS |  |  |  |  | RESPONSIBLE | COMMENTS
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
1 | Identify and determine strategies by means of an integrated approach to address homelessness and the relief measures available, current and future. | Social intervention plan with clear deliverables and defined performance indicators to guide delivery | Ongoing |  è |  è |  è |  è |  è | NCID Manager/ NGOs | This is done comprehensively at the implementation of the CID and then modified continuously
2 | Work in conjunction with local social welfare and job creation organization and develop the delivery of the supplementary services to improve the urban environment | Social intervention plan with clear deliverables and defined performance indicators to guide delivery | Ongoing |  è |  è |  è |  è |  è | NCID Manager/ NGOs | This will be a long term plan of action that will take time to develop – Refer to Program 4-4 and 3-11
3 | Coordinate Social Development programs and initiatives with City Social Development Department | Meet quarterly | Ongoing |  è |  è |  è |  è |  è | NCID Manager
4 | Review Public awareness program on social issues | Updated public awareness program on social issues | Ongoing |  è |  è |  è |  è |  è | NCID Manager
PROGRAM 6 - NCID MARKETING INITIATIVES
NO. | ACTION STEPS | KEY PERFORMANCE INDICATOR | FREQUENCY per year | DURATION IN WEEKS, MONTHS OR YEARS |  |  |  |  | RESPONSIBLE | COMMENTS
|  |  |  | Y1 | Y2 | Y3 | Y4 | Y5
1 | Newsletters / Newsflashes | Informative newsletters distributed. | Quarterly | 4 | 4 | 4 | 4 | 4 | NCID Manager | Also refer to Program 1-16
2 | Regular Press releases in local Newspapers covering: a. Local Development b. Promoting local Projects c. Social Issues | Regular media exposure | Ongoing |  è |  è |  è |  è |  è | NCID Manager
3 | Maintain Website | Up to date and informative website in compliance with CID legislation. | Ongoing |  è |  è |  è |  è |  è | NCID Manager | Refer to Program 1-10
4 | Regular Member visits and meetings | Monthly feedback to NCID Board at Directors Meeting | Ongoing |  è |  è |  è |  è |  è | NCID Manager | Refer to Program 1-18
5 | Maintain the NCID Business Directory and link to website | Up to date directory | Every 6 months | 2 | 2 | 2 | 2 | 2 | NCIDManager
6 | NCID Signage | Signage to be visible and maintained | Ongoing |  è |  è |  è |  è |  è | NCID Manager